## Example
EXAMPLE
EXAMPLE — A completed sample showing how to fill out this canvas for your team.
Phase | Outcome | Strategy | Product | Engineering | Data | Design | Security | Change & Enablement
Discover | Define market problem statements | Drive | Contribute | Enable | Enable | Contribute | Advise | Inform
Discover | Validate customer insights | Contribute | Drive | Enable | Drive | Contribute | Inform | Inform
Discover | Identify technical constraints | Advise | Contribute | Drive | Contribute | Enable | Advise | Inform
Decide | Prioritize use cases | Drive | Contribute | Enable | Advise | Advise | Advise | Inform
Decide | Secure funding and guardrails | Drive | Enable | Inform | Advise | Inform | Advise | Contribute
Decide | Define success metrics | Contribute | Drive | Advise | Contribute | Enable | Inform | Enable
Build | Deliver MVP with acceptance criteria | Inform | Drive | Drive | Contribute | Contribute | Advise | Enable
Build | Design pilot governance | Advise | Contribute | Enable | Contribute | Inform | Advise | Drive
Build | Implement security controls | Inform | Advise | Contribute | Enable | Inform | Drive | Inform
Run | Operationalize support model | Inform | Contribute | Drive | Enable | Inform | Advise | Drive
Run | Measure leading indicators | Advise | Contribute | Enable | Drive | Inform | Advise | Contribute
Run | Maintain SLO compliance | Inform | Advise | Drive | Contribute | Inform | Advise | Inform
Adopt | Activate change plan | Inform | Contribute | Enable | Contribute | Contribute | Inform | Drive
Adopt | Prove value realization | Drive | Contribute | Enable | Drive | Inform | Inform | Drive
Adopt | Scale to additional teams | Contribute | Drive | Enable | Contribute | Enable | Advise | Drive

## Template Section
TEMPLATE SECTION
TEMPLATE — Replace the bracketed placeholders with your team's specific information.
Phase | Outcome | Strategy | Product | Engineering | Data | Design | Security | Change & Enablement
Discover | [INPUT: Outcome statement from your Outcome Definition Worksheet — e.g., 'Define market problem statements'] | [INPUT: D/C/E/A/I — use exactly ONE 'D' per row] | [INPUT: D/C/E/A/I] | [INPUT: D/C/E/A/I] | [INPUT: D/C/E/A/I] | [INPUT: D/C/E/A/I] | [INPUT: D/C/E/A/I] | [INPUT: D/C/E/A/I]
Discover | [INPUT: Additional Discover outcome]
Decide | [INPUT: Decide phase outcome]
Decide | [INPUT: Additional Decide outcome]
Build | [INPUT: Build phase outcome]
Build | [INPUT: Additional Build outcome]
Run | [INPUT: Run phase outcome]
Run | [INPUT: Additional Run outcome]
Adopt | [INPUT: Adopt phase outcome]
Adopt | [INPUT: Additional Adopt outcome]

## Phase Definitions
PHASE DEFINITIONS
REFERENCE — Definitions for each contribution mode and when to use them.
Phase | Purpose | Typical Duration | Key Decisions | Gate Criteria
Discover | Understand the problem and opportunity | 2-4 weeks | Problem worth solving? Users identified? Data available? | Problem validated; Risks assessed; Go/no-go
Decide | Commit resources and define success | 1-2 weeks | Fund this? What scope? What metrics? | Funding approved; Team assigned; Criteria set
Build | Create the solution | 4-12 weeks | Architecture? MVP scope? Quality bar? | Tests pass; Security approved; Ready to deploy
Run | Operate and monitor in production | Ongoing | Scaling decisions? Incident response? | SLOs met; Support ready; Stable operations
Adopt | Drive usage and prove value | 4-8 weeks | Training approach? Success stories? Expansion? | Adoption targets met; Value demonstrated

## Verb Legend
VERB LEGEND
REFERENCE — Definitions for each contribution mode and when to use them.
Code | Verb | Meaning | Decision Rights
D | Drive | Owns outcome; final call within scope | Can decide without escalation
C | Contribute | Delivers work; meets commitments | Can propose; escalates blockers
E | Enable | Provides resources; removes blockers | Prioritizes based on requests
A | Advise | Offers expertise in time-boxed window | Input only; no veto outside window
I | Inform | Receives updates; no active role | Read-only; can escalate concerns

## Rules
RULES
Rule | Description | Why It Matters
One Driver per phase-outcome | Only one D per row | Prevents confusion; clear accountability
Driver can change by phase | Different Ds in Discover vs Build is normal | Match expertise to phase needs
Advisors have windows | Time-box all A assignments | Prevents review bottlenecks
Contributors have deliverables | Every C should have specific outputs | Clarity on expectations
Enable doesn't mean passive | E actively unblocks others | Critical for removing dependencies
Inform is not optional CC | I should be intentional and minimal | Reduces noise; focused updates

## Example Ai Initiative
EXAMPLE AI INITIATIVE
EXAMPLE — A completed sample showing how to fill out this canvas for your team.
Phase | Outcome | Product | Engineering | Data Science | MLOps | Security | Legal | Change
Discover | Identify AI use case | Drive | Enable | Contribute | Inform | Advise | Advise | Inform
Discover | Assess data readiness | Contribute | Enable | Drive | Advise | Advise | Inform | Inform
Decide | Define success criteria | Drive | Contribute | Contribute | Advise | Advise | Contribute | Enable
Decide | Approve ethics framework | Contribute | Advise | Contribute | Inform | Drive | Contribute | Advise
Build | Train and validate model | Advise | Contribute | Drive | Contribute | Advise | Inform | Enable
Build | Build inference pipeline | Inform | Contribute | Contribute | Drive | Advise | Inform | Inform
Run | Monitor model performance | Advise | Contribute | Contribute | Drive | Advise | Inform | Contribute
Run | Manage drift and retraining | Inform | Enable | Drive | Contribute | Advise | Inform | Inform
Adopt | Roll out to users | Drive | Enable | Contribute | Enable | Advise | Advise | Drive
Adopt | Measure business impact | Drive | Advise | Contribute | Enable | Inform | Inform | Contribute

## Example Platform Migration
EXAMPLE PLATFORM MIGRATION
EXAMPLE — A completed sample showing how to fill out this canvas for your team.
Phase | Outcome | Product | Engineering | Platform | Security | Compliance | Finance | Change
Discover | Assess migration scope | Contribute | Contribute | Drive | Advise | Advise | Advise | Inform
Discover | Identify dependencies | Inform | Drive | Contribute | Advise | Inform | Inform | Inform
Decide | Approve migration plan | Drive | Contribute | Contribute | Advise | Advise | Contribute | Enable
Decide | Allocate budget | Contribute | Advise | Advise | Inform | Advise | Drive | Inform
Build | Execute migration | Inform | Contribute | Drive | Contribute | Inform | Advise | Enable
Build | Validate security controls | Inform | Contribute | Contribute | Drive | Contribute | Inform | Inform
Run | Operate new platform | Inform | Contribute | Drive | Advise | Advise | Advise | Contribute
Run | Decommission legacy | Inform | Contribute | Drive | Advise | Contribute | Contribute | Contribute
Adopt | Train teams | Contribute | Enable | Contribute | Advise | Inform | Inform | Drive
Adopt | Confirm cost savings | Contribute | Advise | Contribute | Inform | Inform | Drive | Contribute

## Start Here
C2O OUTCOME MATRIX TEMPLATE
Map contributions across lifecycle phases
Version | 1.0
Generated | December 17, 2025
Source | contribution2outcome.com
Owner | Stark Burns
WHAT'S INSIDE
1 | Example
2 | Template Section
3 | Phase Definitions
4 | Verb Legend
5 | Rules
6 | Example Ai Initiative
7 | Example Platform Migration
C2O CONTRIBUTION MODES
Drive (D) | Owns the outcome and leads execution
Contribute (C) | Actively delivers work toward the outcome
Enable (E) | Provides resources, tools, or support
Advise (A) | Offers expertise when requested
Inform (I) | Kept updated on progress
Full guidance, examples, and updates:
contribution2outcome.com/kb/foundations/canonical-model
💡 Customize team names, metrics, and examples for your organization. Keep the C2O framework elements (D/C/E/A/I, lifecycle phases) as-is.
© 2025 Stark Burns – C2O

## How to Use
HOW TO USE: C2O OUTCOME MATRIX TEMPLATE
⚡ 5-MINUTE QUICK START
1. Look at the "Example" sheet to see what done looks like 2. Copy the "Template" sheet → rename it for your initiative 3. Fill in yellow [INPUT] cells — delete placeholder text as you go 4. Review: exactly ONE "Drive" per row? No empty required fields? 5. Share with your team for validation
📅 WHEN TO USE
As the master view of all outcomes and contributions across your initiative or portfolio.
⏱️ TIME TO COMPLETE
30-45 minutes per outcome; review monthly
✅ BEFORE YOU START
• | Completed Outcome Definition Worksheets for each outcome
• | Org chart or team roster
📋 STEP-BY-STEP
1 | List each outcome as a row
2 | For each outcome, identify the lifecycle phase
3 | Map each function/team to their contribution mode (D/C/E/A/I)
4 | Validate that each row has exactly ONE Driver
5 | Review with all stakeholders for alignment
⚠️ COMMON MISTAKES TO AVOID
| ❌ Matrix becomes stale | → Review and update at each phase gate or monthly
| ❌ Roles instead of names | → Use specific names for accountability; roles are backup
| ❌ Too many outcomes in one matrix | → Split by product area or team for manageability
🎯 SUCCESS LOOKS LIKE
A living document that teams reference when questions arise about 'who owns this?'
🔗 WHERE THIS FITS
Outcome Definition Worksheets for each outcome + Contribution Mapping Canvas → THIS TEMPLATE → Pre-emptive Ownership Pact (POP) or Capacity planning activities
| Complete first: | Outcome Definition Worksheets for each outcome, Contribution Mapping Canvas
| Then move to: | Pre-emptive Ownership Pact (POP), Capacity planning activities
➡️ AFTER COMPLETING
→ | Post in team wiki or shared drive
→ | Reference in Pre-emptive Ownership Pact
→ | Use for capacity planning
👥 QUICK START BY ROLE
| Initiative Driver | Fill out Example sheet first → Define your outcome → Map contributors → Set thresholds
| Sponsor/Executive | Review completed template → Validate Drivers → Approve thresholds → Sign POP
| Contributor | Find your row → Confirm your deliverables → Note review windows → Track signals
| Enabler (Platform/IT) | Check Enable columns → Confirm SLAs → Document dependencies
| Advisor (Legal/Security) | Review Advise columns → Define advice windows → Set response SLAs
🔧 TROUBLESHOOTING
| "Decisions are stalling" | → Check: Is there exactly one Driver per phase? Are thresholds defined?
| "Teams argue about who owns what" | → Revisit the Contribution Map; clarify D vs. C distinction
| "Advisors are blocking progress" | → Define time-boxed review windows; silence = consent after deadline
| "Nobody knows the current status" | → Set up weekly signal reviews; link to a live dashboard
| "Template feels too complex" | → Start with just Phase 1 (Discover) → Add phases incrementally
| "Stakeholders pushing back on C2O" | → Show the "before/after" examples; focus on clarity gains
💡 WHITE-LABELING: You may customize team names, metrics, and examples. Keep the C2O framework elements (D/C/E/A/I modes, 5 lifecycle phases) as-is.