## Example
EXAMPLE
EXAMPLE — A completed sample showing how to fill out this canvas for your team.
Phase | Drive | Contribute | Enable | Advise | Inform
Discover | Product Lead (Alice) | Research, Design | Platform | Security, Legal | Leadership
Decide | Product Lead (Alice) | Engineering, Finance | Platform, Architecture | Risk, Compliance | Leadership
Build | Engineering Lead (Bob) | Design, QA, DevOps | Platform, CI/CD | Security, Product | Leadership, Support
Run | SRE Lead (Carlos) | Engineering, Support | Platform, Monitoring | Security, Product | Leadership
Adopt | Product Lead (Alice) | PMM, Training, Champions | HR, Communications | Customer Success | All Teams

## Template Section
TEMPLATE SECTION
TEMPLATE — Replace the bracketed placeholders with your team's specific information.
Phase | Drive | Contribute | Enable | Advise | Inform
Discover | [INPUT: ONE person/role who owns this phase — e.g., 'Product Lead (Alice)'] | [INPUT: Teams actively delivering — e.g., 'Research, Design'] | [INPUT: Teams providing resources — e.g., 'Platform'] | [INPUT: SMEs consulted — e.g., 'Security, Legal'] | [INPUT: Kept updated — e.g., 'Leadership']
Decide | [INPUT: ONE Driver] | [INPUT: Contributors] | [INPUT: Enablers] | [INPUT: Advisors] | [INPUT: Informed]
Build | [INPUT: ONE Driver] | [INPUT: Contributors] | [INPUT: Enablers] | [INPUT: Advisors] | [INPUT: Informed]
Run | [INPUT: ONE Driver] | [INPUT: Contributors] | [INPUT: Enablers] | [INPUT: Advisors] | [INPUT: Informed]
Adopt | [INPUT: ONE Driver] | [INPUT: Contributors] | [INPUT: Enablers] | [INPUT: Advisors] | [INPUT: Informed]

## Verb Definitions
VERB DEFINITIONS
REFERENCE — Definitions for each contribution mode and when to use them.
Verb | Definition | Responsibility | Time Commitment | Accountability
Drive | Owns the outcome and ensures delivery | Makes final decisions within scope; Removes blockers; Coordinates contributors | High (50-100% of time) | Accountable for success/failure
Contribute | Actively delivers work toward outcome | Produces deliverables; Meets commitments; Escalates blockers | Medium-High (25-75%) | Responsible for quality of deliverables
Enable | Provides resources and infrastructure | Supplies tools/access; Removes dependencies; Maintains platforms | Variable (on-demand) | Responsible for unblocking others
Advise | Offers expertise when consulted | Reviews within window; Provides recommendations; Raises risks | Low (time-boxed windows) | Responsible for input quality (not outcome)
Inform | Receives updates on progress | Stays aware; Provides feedback if requested; Escalates concerns | Minimal (read-only) | No direct accountability

## Advisor Windows
ADVISOR WINDOWS
TIMING — When to engage advisory functions during each lifecycle phase.
Phase | Security Review | Legal Review | Finance Review | Architecture Review | Risk Review
Discover | Week 1-2 | As needed | Week 2-3 | Week 1 | Week 2
Decide | Gate pre-read | Contract review | Budget approval | Design review | Risk assessment
Build | Security scan (continuous) | N/A | Variance check | Code review (as needed) | Milestone check
Run | Incident response | Compliance audit | Cost monitoring | Capacity review | Incident review
Adopt | Pen test (pre-launch) | Terms review | ROI validation | N/A | Post-mortem

## Handoff Checklist
HANDOFF CHECKLIST
CHECKLIST — Required evidence and criteria for phase transitions.
From Phase | To Phase | Driver Handoff | Evidence Required | Gate Criteria
Discover | Decide | Product Lead stays or hands to Business Sponsor | Problem validation, User research, Opportunity sizing | Outcome defined, Risks identified, Sponsor approval
Decide | Build | Business Sponsor to Engineering Lead | Business case, Success criteria, Resource commitment | Funding approved, Team assigned, Architecture blessed
Build | Run | Engineering Lead to SRE/Ops Lead | Runbooks, Monitoring setup, On-call rotation | All tests pass, Security review complete, Deployment verified
Run | Adopt | SRE Lead to Change/Adoption Lead | Performance baselines, Support readiness, Training materials | SLOs met, Support trained, Users onboarded

## Anti Patterns
ANTI PATTERNS
WARNING — Common mistakes to avoid and how to address them.
Pattern | Symptom | Fix
No Driver | Decisions stall; no one removes blockers | Assign single accountable Driver per phase
Multiple Drivers | Conflicting decisions; finger-pointing | One Driver only; others Contribute
Driver does everything | Burnout; bottleneck | Delegate to Contributors; trust the team
Advisors as blockers | Reviews never complete; scope creep | Time-box windows; silence = consent
Everyone Informed | Meeting overload; no one reads updates | Limit Inform to true stakeholders
Contributors without clarity | Duplicate work; gaps in delivery | Define specific contributions upfront

## Common Mappings
COMMON MAPPINGS
PATTERNS — Typical contribution mappings by organizational function.
Function | Typical Verb Pattern | When They Drive | When They Contribute
Product Management | Drive (Discover, Decide, Adopt) | Problem definition, prioritization | Technical decisions, operations
Engineering | Drive (Build, Run) | Technical implementation, operations | Discovery research, adoption
Design | Contribute (all phases) | UX-critical initiatives | Standard feature work
Data/Analytics | Enable + Contribute | Data products, experimentation | Reporting, insights
Security | Advise (all phases) | Security incidents, compliance mandates | Standard reviews
Legal | Advise (Decide, Adopt) | Contract negotiations, compliance | Standard reviews
Finance | Enable + Advise | Budget decisions | Planning, reporting
HR/People | Enable (Adopt) | Org changes, culture initiatives | Training, communications

## Start Here
CONTRIBUTION MAPPING CANVAS
Visualize team contributions by phase
Version | 1.0
Generated | December 17, 2025
Source | contribution2outcome.com
Owner | Stark Burns
WHAT'S INSIDE
1 | Example
2 | Template Section
3 | Verb Definitions
4 | Advisor Windows
5 | Handoff Checklist
6 | Anti Patterns
7 | Common Mappings
C2O CONTRIBUTION MODES
Drive (D) | Owns the outcome and leads execution
Contribute (C) | Actively delivers work toward the outcome
Enable (E) | Provides resources, tools, or support
Advise (A) | Offers expertise when requested
Inform (I) | Kept updated on progress
Full guidance, examples, and updates:
contribution2outcome.com/kb/capabilities/contribution-mapping
💡 Customize team names, metrics, and examples for your organization. Keep the C2O framework elements (D/C/E/A/I, lifecycle phases) as-is.
© 2025 Stark Burns – C2O

## How to Use
HOW TO USE: CONTRIBUTION MAPPING CANVAS
⚡ 5-MINUTE QUICK START
1. Look at the "Example" sheet to see what done looks like 2. Copy the "Template" sheet → rename it for your initiative 3. Fill in yellow [INPUT] cells — delete placeholder text as you go 4. Review: exactly ONE "Drive" per row? No empty required fields? 5. Share with your team for validation
📅 WHEN TO USE
At the start of any initiative to clarify who contributes what during each lifecycle phase.
⏱️ TIME TO COMPLETE
45-60 minutes for initial mapping; 15 minutes for updates
✅ BEFORE YOU START
• | Defined outcome statement (use Outcome Definition Worksheet)
• | List of involved teams/roles
📋 STEP-BY-STEP
1 | Start with the Example sheet to understand the format
2 | Copy the Template sheet and rename it for your initiative
3 | Fill in your outcome and lifecycle phase for each row
4 | Assign exactly ONE Driver (D) per phase—this is non-negotiable
5 | Add Contributors (C), Enablers (E), Advisors (A), and Informed (I) as needed
⚠️ COMMON MISTAKES TO AVOID
| ❌ Multiple Drivers per phase | → Only one person/team can Drive—others should Contribute
| ❌ Everyone is Informed on everything | → Be selective—too many I's creates noise
| ❌ Skipping phases | → Every phase needs at least a Driver
🎯 SUCCESS LOOKS LIKE
Clear accountability with no gaps or overlaps; team members can answer 'who do I go to?' instantly
🔗 WHERE THIS FITS
Outcome Definition Worksheet → THIS TEMPLATE → Pre-emptive Ownership Pact (POP) or C2O Outcome Matrix
| Complete first: | Outcome Definition Worksheet
| Then move to: | Pre-emptive Ownership Pact (POP), C2O Outcome Matrix
➡️ AFTER COMPLETING
→ | Share with all mapped stakeholders for validation
→ | Store alongside your Pre-emptive Ownership Pact
→ | Review at each phase gate
👥 QUICK START BY ROLE
| Initiative Driver | Fill out Example sheet first → Define your outcome → Map contributors → Set thresholds
| Sponsor/Executive | Review completed template → Validate Drivers → Approve thresholds → Sign POP
| Contributor | Find your row → Confirm your deliverables → Note review windows → Track signals
| Enabler (Platform/IT) | Check Enable columns → Confirm SLAs → Document dependencies
| Advisor (Legal/Security) | Review Advise columns → Define advice windows → Set response SLAs
🔧 TROUBLESHOOTING
| "Decisions are stalling" | → Check: Is there exactly one Driver per phase? Are thresholds defined?
| "Teams argue about who owns what" | → Revisit the Contribution Map; clarify D vs. C distinction
| "Advisors are blocking progress" | → Define time-boxed review windows; silence = consent after deadline
| "Nobody knows the current status" | → Set up weekly signal reviews; link to a live dashboard
| "Template feels too complex" | → Start with just Phase 1 (Discover) → Add phases incrementally
| "Stakeholders pushing back on C2O" | → Show the "before/after" examples; focus on clarity gains
💡 WHITE-LABELING: You may customize team names, metrics, and examples. Keep the C2O framework elements (D/C/E/A/I modes, 5 lifecycle phases) as-is.