Pre-emptive Ownership Pact (POP)

Governance template for outcome alignment

contribution2outcome.com

December 17, 2025

Version 1.0

Owner: Stark Burns

SOURCE REFERENCE

Full guidance, examples, and updates:

contribution2outcome.com/kb/framework-method/decision-rights/charters-and-matrices

# Executive Summary

| Overview | Fillable template for creating Pre-emptive Ownership Pacts with decision protocols. |
| --- | --- |

A POP is a lightweight agreement that establishes decision rights, thresholds, and escalation triggers before work begins. It prevents "who owns this?" debates by making accountability explicit per phase.

## Quick Reference: POP vs Traditional Charters

| Traditional Charter | Pre-emptive Ownership Pact |
| --- | --- |
| Lists all stakeholders equally | Names one Driver per phase |
| Vague "accountability" statements | Explicit thresholds and triggers |
| Static roles throughout | Dynamic verbs that change by phase |
| Escalation by opinion | Escalation by threshold |
| Updated rarely | Refreshed at phase gates |

Key difference: A POP assigns authority before decisions arise, not during debates.

## POP Quality Checklist

Before finalizing, verify:

• One Driver named per phase (never co-Drivers)

• Thresholds are numeric or objective (not "significant" or "major")

• Escalation actions are explicit (rollback, pause, escalate)

• Advice windows have SLAs (24–72h)

• Record format is defined (five bullets + links)

• Review cadence is scheduled

• Sponsor can resolve escalations

## Document Context

| Document | Reference |
| --- | --- |
| Outcome Definition Worksheet | [INPUT: Link to your Outcome Definition Worksheet — the foundation for this POP] |
| Contribution Mapping Canvas | [INPUT: Link to your Contribution Mapping Canvas] |
| C2O Matrix | [INPUT: Link to your C2O Outcome Matrix, if applicable] |
| Related POPs | [INPUT: Links to related initiative POPs, if this is part of a larger program] |

## Part 1: Initiative Summary

| Field | Your Input |
| --- | --- |
| Initiative Name | [INPUT: Your project/product name — e.g., "Mobile Payment Redesign"] |
| Sponsor | [INPUT: Executive accountable for initiative success — e.g., "Alice Chen (VP Product)"] |
| Timeframe | [INPUT: Start and end dates or quarters — e.g., "Q1-Q2 2025"] |
| Primary Outcome | [INPUT: One sentence — e.g., "New users complete first purchase in <5 min without support"] |
| Success Signals | [INPUT: Key metrics — e.g., "D7 activation ≥40%; Support tickets <2% of transactions"] |
| Key Constraints | [INPUT: Budget, timeline, compliance, dependencies] |

## Part 2: Outcome Definitions

Define 1–3 measurable outcomes. See the Outcome Definition Worksheet for guidance.

### Outcome 1 (Primary)

| Field | Value |
| --- | --- |
| Outcome Statement | "[Who] will [observable behavior] by [when], evidenced by [signal]" |
| Acceptance Criteria | 1. <br> 2. <br> 3. |
| Leading Signals |  |
| Lagging Signals |  |

### Outcome 2 (Secondary, optional)

| Field | Value |
| --- | --- |
| Outcome Statement |  |
| Acceptance Criteria | 1. <br> 2. |
| Leading Signals |  |
| Lagging Signals |  |

## Part 3: Contribution Map by Lifecycle Phase

### C2O Verbs Reference

| Verb | Meaning | Key Trait |
| --- | --- | --- |
| Drive | Accountable for phase outcome; decides within thresholds | One Driver per phase |
| Contribute | Delivers the work (code, research, design) | Material delivery, not opinions |
| Enable | Provides tools, platforms, expertise | Partners, not gatekeepers |
| Advise | Provides input within bounded windows | Input to decisions, not vetoes |
| Inform | Receives updates; no action required | One-way communication |

### Contribution Matrix

| Phase | Drive (D) | Contribute (C) | Enable (E) | Advise (A) | Inform (I) |
| --- | --- | --- | --- | --- | --- |
| Discover |  |  |  |  |  |
| Decide |  |  |  |  |  |
| Build |  |  |  |  |  |
| Run |  |  |  |  |  |
| Adopt |  |  |  |  |  |

Guidance:

• Name specific people, not teams

• Each phase must have exactly one Driver

• Contributors do material work; Advisors provide input

• Enablers unblock; they don't approve

### Example Matrix (Self-Serve Onboarding)

| Phase | Drive (D) | Contribute (C) | Enable (E) | Advise (A) | Inform (I) |
| --- | --- | --- | --- | --- | --- |
| Discover | Alice (PM) | Research, UX | Platform | Security | Leadership |
| Decide | Alice (PM) | Engineering, UX | Platform | Architecture | Leadership |
| Build | Bob (TL) | Engineering, QA | Platform, DevOps | Security, Privacy | PM, Leadership |
| Run | Carlos (SRE) | Engineering, Support | Platform | Security | PM |
| Adopt | Alice (PM) | PMM, Support | Training | Leadership | Engineering |

## Part 4: Phase Charter (Current Phase)

Fill this out for the current phase. Create a new charter when you transition phases.

### Phase Information

| Field | Value |
| --- | --- |
| Phase | Discover / Decide / Build / Run / Adopt |
| Driver | [Name] |
| Sponsor | [Name] |
| Phase Window | [Start date] → [End date] |

### Scope

| In Scope | Out of Scope |
| --- | --- |

### Decision Authority (Within Thresholds)

| Decision Type | Authority |
| --- | --- |
| [Slice scope adjustments] | Driver decides |
| [Resource allocation] | Driver decides |
| [Technical trade-offs within budget] | Driver decides |
| [Scope +20% or new PII] | Escalate to Sponsor |

### Thresholds & Escalation Triggers

| Trigger | Threshold | Action | Owner |
| --- | --- | --- | --- |
| Schedule slip | >1 week | Hold; Driver proposes recovery | Driver |
| Cost variance | >10% of estimate | Escalate with options | Driver → Sponsor |
| Risk severity | Critical or compliance | Escalate immediately | Driver → Sponsor |
| Signal off-target | >25% | Escalate with recommendation | Driver → Sponsor |

Threshold Actions:

• Green (Expand): Within thresholds → Driver decides locally; inform stakeholders

• Yellow (Hold): 10–25% off target → Driver proposes; Sponsor approves

• Red (Escalate): >25% off target OR guardrail violated → Escalate with options + recommendation

## Part 5: Advisors & Advice Windows

### Advisor Matrix

| Role | Contact | SLA | Topic | Format |
| --- | --- | --- | --- | --- |
| Security |  | 48h | Data handling, auth | Checklist |
| Privacy |  | 48h | Consent, retention | Checklist |
| Legal |  | 72h | Terms, contracts | Review |
| Architecture |  | 48h | Integration patterns | Review |
| SRE/Platform |  | 24h | Alerts, runbooks | Checklist |

### Advice Window Protocol

1. Driver opens advice window with specific questions (not open-ended)

2. Advisors respond within SLA using checklists, not meetings

3. Driver closes window and makes decision

4. Decision recorded with rationale and links

Good advice question: "Does this data flow require a DPIA? Here's the flow diagram."
Poor advice question: "What do you think about our approach?"

## Part 6: Decision Protocols

### Decision Record Format

Every decision uses this five-bullet format:

1. Context: What prompted this decision?

2. Decision: What did we decide?

3. Rationale: Why this option over alternatives?

4. Trade-offs: What did we give up?

5. Follow-ups: What actions remain?

Required links: Dashboard, relevant docs, related decision IDs

### Record Example

## DR-2025-042: Rollout Pacing
1. **Context:** Error rate elevated after 10% rollout
2. **Decision:** Hold at 10% for 48h; add circuit breaker
3. **Rationale:** User impact contained; root cause identified
4. **Trade-offs:** Delayed full rollout by 3 days
5. **Follow-ups:** Add latency alert (Bob, by Friday)
Links: [Dashboard](link) | [Incident](link) | [PR #1234](link)

### Escalation Package Requirements

When escalating, include:

• Current status vs. target

• 2–3 options with trade-offs

• Driver's recommendation

• Decision deadline

• Impact of delay

## Part 7: Risks & Dependencies

| Risk / Dependency | Likelihood | Impact | Mitigation | Owner | Status |
| --- | --- | --- | --- | --- | --- |
|  | H / M / L | H / M / L |  |  | Open / Mitigated |
|  | H / M / L | H / M / L |  |  | Open / Mitigated |
|  | H / M / L | H / M / L |  |  | Open / Mitigated |

## Part 8: Feedback & Review Cadence

| Ritual | Frequency | Duration | Owner | Purpose |
| --- | --- | --- | --- | --- |
| Weekly Update | Weekly | Async (<200 words) | Driver | Status, decisions, signals |
| Contributor Sync | Weekly | 30 min | Driver | Unblock, coordinate |
| Enable Council | Bi-weekly | 30 min | Enablers | Prerequisites, SLAs |
| Phase Gate | At transitions | 45 min | Driver + Sponsor | Go/no-go with evidence |
| Retrospective | End of phase | 60 min | Driver | Improve practices |

### Weekly Update Template

## [Initiative] — Week [N] Update
**Status:** On Track / At Risk / Off Track
**Decision this week:** [Expand/Hold/Iterate] — [DR-ID]
**Signals:**
- [Leading signal]: [current] vs. [target] — [status]
- [Lagging signal]: [current] vs. [baseline] — [status]
**Guardrails:** [All green / Issue: brief description]
**Next week:**
- [Action 1]
- [Action 2]
**Links:** [Dashboard] | [Decision Record] | [Gate Pre-read]

## Part 9: Signatures & Acknowledgment

By signing, we agree to:

• Abide by the decision rights and thresholds in this POP

• Escalate when triggers are met

• Update this POP at phase transitions

• Record decisions in the standard format

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Sponsor |  |  |  |
| Discover Driver |  |  |  |
| Decide Driver |  |  |  |
| Build Driver |  |  |  |
| Run Driver |  |  |  |
| Adopt Driver |  |  |  |
| Enable Lead(s) |  |  |  |

## Worked Examples

### Example 1: Product Initiative (Self-Serve Onboarding)

Initiative: Self-serve onboarding for new accounts
Outcome: New accounts reach first value in ≤10 min without assistance, with 20% activation lift by day 7

| Phase | Driver | Key Threshold |
| --- | --- | --- |
| Discover | Product Lead | Discovery complete when problem clarity score ≥4/5 |
| Decide | Product Lead | Decide when 3+ options evaluated with trade-offs |
| Build | Tech Lead | Escalate if error-budget burn >35% or cost +10% |
| Run | SRE Lead | Escalate if MTTR >30 min or incident rate doubles |
| Adopt | Product Lead | Scale when activation delta credible |

### Example 2: Platform Migration

Initiative: Migrate payment service to new platform
Outcome: Zero-downtime migration with <0.1% transaction failure rate

| Phase | Driver | Key Threshold |
| --- | --- | --- |
| Discover | Architecture Lead | Discovery complete when risk assessment approved |
| Decide | Engineering Director | Decide when cost model validated |
| Build | Migration Lead | Escalate if test coverage <95% or latency +20% |
| Run | SRE Lead | Escalate if error rate >0.05% during cutover |
| Adopt | Platform Lead | Scale when 30-day stability confirmed |

### Example 3: Compliance Change

Initiative: Implement data retention policy
Outcome: Zero critical violations with stable portal NPS (±5 points)

| Phase | Driver | Key Threshold |
| --- | --- | --- |
| Discover | Compliance Lead | Discovery complete when all data flows mapped |
| Decide | Legal Lead | Decide when policy approved by counsel |
| Build | Engineering Lead | Escalate if any PII flow undocumented |
| Run | Ops Lead | Escalate if retention job SLO <99.9% |
| Adopt | Compliance Lead | Scale when audit confirms zero findings |

## Common Failure Modes

| Anti-Pattern | Symptom | Fix |
| --- | --- | --- |
| Co-Drivers | Two people share authority; decisions stall | Name one Driver per phase; other becomes Advisor |
| Advice creep | Open-ended input windows; meetings proliferate | Explicit questions with SLAs; link-only responses |
| Escalation by opinion | "I think this is important" triggers escalation | Publish numeric thresholds; require options + recommendation |
| Vague thresholds | "Major" or "significant" language | Use numbers: +10%, >25%, >1 week |
| Stale POP | Same document from kickoff to launch | Refresh at phase transitions; tune monthly |
| Shadow boards | Decisions made in side conversations | Reference DR IDs in weeklies; audit decision log |

## POP Effectiveness Metrics

| Metric | Target | How to Measure |
| --- | --- | --- |
| Decision latency | ≤48h from raised to recorded | Track time from question to DR |
| Escalation rate | Trending down | Count escalations per phase |
| Advice turnaround | Within SLA (24–72h) | Track response times |
| Re-litigation rate | <10% of decisions | Count decisions revisited |
| POP refresh | At every phase gate | Audit update timestamps |

## Quick-Start: 15-Minute POP

If you don't have time for a full POP workshop:

| Min | Step | Output |
| --- | --- | --- |
| 0–3 | State outcome and name Sponsor | One-sentence outcome |
| 3–6 | Name Driver for first phase | Driver with authority scope |
| 6–9 | Set one threshold and action | "If X exceeds Y, escalate" |
| 9–12 | Identify one Enabler and one Advisor | Names with SLAs |
| 12–15 | Set first review date | Date on calendar |

Expand to full POP at first phase gate.

## Next Steps

1. Complete this POP with Driver, Sponsor, and key Contributors

2. Publish in your initiative wiki; link from weekly updates

3. Review at phase gates and update Drivers/thresholds as needed

4. Tune monthly based on decision latency and escalation patterns

5. Retrospect at initiative end; codify practices for next team

Use this template with the Charters & Matrices guide in the C2O Knowledge Base for facilitation scripts and additional examples.